## Sheet1
Daily Stand-up Meeting Report
Week: Aug 28 - Sept 3
Project Name:
Team Name: ## The Minions
| Monday | Wednesday | Friday
Ramu Devarashetti | 1)Finalized project idea | 1) Finalized the TechStack. Backend: Python FastAPI Frontend: RecatJs, HTML 5, CSS 3. Database: As of Now MySQL or MariaDB. | 1)Tried out Hello world Flask APP. Initial discussion for ERD. DB Tables schema.
| 2) Try out sample Hello world app and structure the project. Discuss Database Entities as a Group. (ERD). | 2) Try out sample Hello world app and structure the project. Discuss Database Entities as a Group. (ERD). | 2) Help Migrating User Schema with FastAPI Backend. Finalize ORM for the Python FastAPI.
| 3) NA | 3) NA | 3)NA
Narendar Reddy Katta | 1)Finalized project idea | 1) Finalized the TechStack. Backend: Python FastAPI Frontend: RecatJs, HTML 5, CSS 3. Database: As of Now MySQL or MariaDB | 1) Started creating rough sketches for project layout
| 2) Started exploring more about project idea | 2) Finalized color combinations we have to use | 2)Finalized font to use for web apps
| 3)NA | 3) NA | 3) NA
Nikhil Chowdary Bonthu | 1)Finalizing project idea | 1) Finalized the TechStack. Backend: Python FastAPI Frontend: RecatJs, HTML 5, CSS 3. Database: As of Now MySQL or MariaDB | Started creating a basic logo's for project.
| 2)Brusing up skill set | 2) Started practcing react library | With help of team members started working on fornt end and database.
| 3) NA | 3) NA | Gather more details about Project.
Shashank Pasumarthi | 1) Finalizing project idea | 1) Finalized the TechStack. Backend: Python FastAPI Frontend: RecatJs, HTML 5, CSS 3. Database: As of Now MySQL or MariaDB | 1)Research for user ERD.
| 2)Started exploring database conceptsand ERD | 2) Start with the ERD of the database. | 2)User table ERD design.
| 3)NA | 3) NA | 3)NA
Manikanta Gaddameda | 1) Finalizing project idea | 1) Finalized the TechStack. Backend: Python FastAPI Frontend: RecatJs, HTML 5, CSS 3. Database: As of Now MySQL or MariaDB | 1)Working on ERD with the help of Teammates
| 2) Started exploring database conceptsand ERD | 2) Start with the ERD of the database. | 2)Started creating a basic logo's for project.
| 3)NA | 3)NA | 3)NA
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?

## Sheet2
Daily Stand-up Meeting Report
Week: Sep 5th - Sept 9th
Project Name: Bearcat Resident Connect
Team Name: ## The Minions
| Monday | Wednesday | Friday
Ramu Devarashetti | NA | Finalized Database Entities for User and Addresses | Tried Python SqlAlchemy ORM. Research on Layout Design.
| NA | Try Implementing ERD Schema in Python using SqlAlchemy | Try Implementing Other Database Entitries.
| NA | 3) NA | NA
Narendar Reddy Katta | NA | 1) Finalized font family to use for application | 1) Started designing wire frame for application
| NA | 2) Need to finalize layout for application | 2) Need to implement for all pages
| NA | 3) NA | 3) NA
Nikhil Chowdary Bonthu | NA | 1) Start working on the front end layouts to implement in application | 1) Designed layout for login page
| NA | 2) Came up with font and color code to add for application | 2) Going through React libraries which we are going to use in our project
| NA | 3) Need to finalize layout for application | 3)NA
Shashank Pasumarthi | NA | 1) Created sketch for database entities for user and address | 1) Working with remaining entities in the ERD of the database.
| NA | 2) Complete with remaining entities in the ERD of the database. | 2) Continue to work on the ERD
| NA | 3) NA | 3) NA
Manikanta Gaddameda | NA | 1) Practiced ER diagram in lucid chart | 1)Started working on ERD related to our project
| NA | 2) Drew lucid chart with help of teammates | 2)Gathering properties information for our project
| NA | 3) Need to implement ERD for remaining entities
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?

## Sheet3
Daily Stand-up Meeting Report
Week: Sep 12th - Sept 16th
Project Name: Bearcat Resident Connect
Team Name: ## The Minions
| Monday | Wednesday | Friday
Ramu Devarashetti | 1) Rough ERD schemas for remaing entities. Frontend Layout Mockups help. | 1) Implemented User model mapping in Python. | 1) Started working on Reactjs.
| 2) Implement Python ERD Model Mapping. | 2) Integrate frontend and backend. | 2) Integrate frontend and backend.
| NA | NA | NA
Narendar Reddy Katta | 1) Designing layouts in PSD for login and signup are done | 1) Integrating front end code in react | 1) Integrating front end code in react
| 2) Need to implement layout for dashboard as well | 2) Need to inegrate backend apis in react | 2) Need to inegrate backend apis in react
| 3)NA | 3) NA | 3) NA
Nikhil Chowdary Bonthu | Designed login page in photoshop | 1) Designed a basic layout for dashboard | 1)Integrating front end code in react library
| Need to do remaining layouts in photoshop | 2) Need to integrate backend apis in react library | 2) Need to integrate backend apis in react library
| NA | 3) NA | 3) NA
Shashank Pasumarthi | Completed remaining entities of the ER diagram | 1)NA | 1)Writing python code for the ERD
| help in backend code | 2)NA | 2) Completion of python code for ERD
| NA | 3)NA | 3)NA
Manikanta Gaddameda | Started designing layouts for application. | 1) Practicing Test cases for our application | 1) implemented test case for our project
| Started helping in front end. | 2) Implementing test cases for our application | 2) Need to write more test cases
| NA | NA | NA
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?

## Sheet4
Daily Stand-up Meeting Report
Week: Sep 19th - Sept 25th
Project Name: Bearcat Resident Connect
Team Name: ## The Minions
| Monday | Wednesday | Friday
Ramu Devarashetti | Worked on Unit Testing and React Helloworld App and some React Tutorials. | Unit Testing. | Continue APIs for User Postings.
| Improve test coverage and also work on Integration of UI with Backend. | APIs for User Postings. | Continue the same.
| NA | NA | NA
Narendar Reddy Katta | Integrating html code in Angular | Integrating html code in react | Integrating registration api in angular
| Need to integrare bacnekd in Angular | Need to integrare bacnekd in react | Need to integrate login as well
| Rendering component inside component | Rendering component inside component | NA
Nikhil Chowdary Bonthu | Integrating html code in Angular | Integrating html code in Angular | Reviewing what all libraries avilable in angular for authentication
| Integrating with backend for authentication reviewing what all are libraries available | integrating with the backend for authentication and assessing the library options | Need to write signup validations.
| NA | No obstacles | NA
Shashank Pasumarthi | User table ERD design | Pyhton code for ERD | Python code for remaining entities
| python code for remaining entities for ERD | Python code for remaining entities | input and output schemas
| NA | NA | NA
Manikanta Gaddameda | Implemeting test cases in application | Practicing test cases | Practicing Angular routing
| Need to write test cases for reaming | Implementing test cases for our project | Writing validations for login signup page
| NA | NA | NA
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?

## Sheet5
Daily Stand-up Meeting Report
Week: Sep 26th - Sep 30th
Project Name: Bearcat Resident Connect
Team Name: ## The Minions
| Monday | Wednesday | Friday
Ramu Devarashetti | Presentation on TeckStack of BRC | Worked on UI Integration. | Continue on the workaround principles to connect with UI.
| Work on UI Integration. | Continue on the same. | Continue on the same.
| NA | Issues connecting with Angular. | NA
Narendar Reddy Katta | Presentation on TeckStack of BRC | Routing for login and signup | Routing for login and signup
| Integrating registration api in angular | Writing vaidations for login | Writing vaidations for login
| NA | NA | NA
Nikhil Chowdary Bonthu | Presentation on TeckStack of BRC | Reviewing routing concepts | Reviewing routing concepts
| Writing validations for signup page | Writing validations for signup page | Writing validations for signup page
| NA | NA | NA
Shashank Pasumarthi | input and output schemas | User postings | API validation
| User postings | API validation | Schema Design
| NA | NA | NA
Manikanta Gaddameda | Prepared for the Worksop presentation | Writing validations for login signup page | Working on Angular
| Writing validations for login signup page | Practicing Angular routing | Implemeting test cases in application
| NA | NA | NA
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?